## Task_subtasks
Task Numbers | Main Tasks | Sub Tasks | Type | Format | Responsible | Start | End | Task Leader | DMP comments and queries
D1.1 | Long-term post seismic deformation Andaman-Sumatra |  | Dataset, report | CSV | UoE, INCOIS, EOS | M01 | M24 | Karen Lythgoe
D1.1 | Long-term post seismic deformation Andaman-Sumatra | Generation of stochastic source, Scenarios for the Andaman, Sumatra subduction zone | Dataset, report | CSV | INCOIS | M15 | M24 | Dipankar Saikya
D1.4.1 | EQ-induced PTHA (nation-wide) |  | Dataset | CSV | INCOIS | M19 | M32 | Siva Srinivas
D1.4.1 | EQ-induced PTHA (nation-wide) | Numerical model need to be run after the Scenarios generation | Dataset | CSV | INCOIS | M19 | M32 | Siva Srinivas
D1.4.2 | EQ-induced PTHA (site-specific) |  | Dataset | CSV | INCOIS | M19 | M32 | Siva Srinivas
D1.4.2 | EQ-induced PTHA (site-specific) | Numerical model need to be run after the Scenarios generation | Dataset | CSV | INCOIS | M19 | M32 | Siva Srinivas
D1.4.3 | Conditional Landslide-induced PTHA |  | Dataset | esrii ascii/ python code | NGI | M01 | M35 | Finn Lovholt | It would make sense to keep scripts and background data for producing the datasets. The sets themselves can be very large and unconvenient to store as big data. This is even more the case for the simulations than for the scenarios. However, key processed outputs that are compressed should be kept. Done updating DMP.
D1.4.4 | EQ-induced Inundation Distance and Runup (nation-wide) |  | Dataset | CSV | INCOIS | M19 | M39 | Siva Srinivas
D1.4.4 | EQ-induced Inundation Distance and Runup (nation-wide) | Numerical model need to be run after the Scenarios generation | Dataset | CSV | INCOIS | M19 | M39 | Siva Srinivas
D1.4.5 | EQ-induced Inundation Maps (site-sepcific) |  | Dataset | CSV | INCOIS | M19 | M39 | Siva Srinivas
D1.4.5 | EQ-induced Inundation Maps (site-sepcific) | Numerical model need to be run after the Scenarios generation | Dataset | CSV | INCOIS | M19 | M39 | Siva Srinivas
D1.5 | Hourly Exposure Maps |  | Dataset | CSV, GIS-vectors | UCL | M30 | M45 | Saman/Mahendra
D1.5 | Hourly Exposure Maps | Generation of the human exposure maps and human mobility | Dataset | CSV, GIS-vectors | UCL | M30 | M45 | Saman/Mahendra
D1.6 | PTRA (site-specific) |  | Dataset | CSV | UCL, INCOIS | M30 | M48 | Fatemeh
D2.1 | Rapid source characterization based on GNSS test and validation |  | Report, software | CSV | INCOIS | M20 | M30 | Patanjali/Sunanda
D2.1 | Rapid source characterization based on GNSS test and validation | Develpoment of GNSS Data pre-processing and QC modules using Open Source Softwares / Python Frameworks | Report, software | CSV | INCOIS | M20 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Developoment of GNSS Data processing Pacakge for realtime coseismic displacements form 35 GNSS stations of A&N Network | Report, software | CSV | INCOIS | M21 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Validation of Processing results of 'Real-time Data Proessing againist Trimble Integrity Manger software Modules - Rapid motion as well as Network Motion Engine results | Report, software | CSV | INCOIS | M22 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Development of Co-sesmic Fault model Estimation Module using Python framework | Report, software | CSV | INCOIS | M23 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Testing of Co-seismic Fault model Estimation module against Hisotrical events and a few hypothetical events at A&N Islands | Report, software | CSV | INCOIS | M24 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Development of Slip-Distribution model Estimation Module using Python framework | Report, software | CSV | INCOIS | M25 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Testing of Slip-Distribution model Estimation module against Hisotrical events and a few hypothetical events at A&N Islands | Report, software | CSV | INCOIS | M26 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Pacakaging and Validation of Rapid Source charactatszation software along with Scientific & Techincal Documentation | Report, software | CSV | INCOIS | M27 | M30 | Patanjali
D2.1 | Rapid source characterization based on GNSS test and validation | Submission / Distribution / Operationlisation of Rapid Source characterization software | Report, software | CSV | INCOIS | M28 | M30 | Patanjali
D2.2 | ML-based Tsunami inundation emulation training, test, validations |  | Report, Dataset, Data Product | netcdf/ python code | NGI,UCL | M01 | M48 | Finn | Emulator code and datasets for some specific sites where we do the training. Done updating DMP.
D2.3 | PTF test and validation |  | Report, dataset | CSV | INCOIS, NGI | M01 | M48 | Patanjali/Finn
D2.3 | PTF test and validation |  | Report, dataset | CSV | INCOIS, NGI | M01 | M48 | Patanjali/Finn
D2.3 | PTF test and validation |  | Report, dataset | CSV | INCOIS, NGI | M01 | M48 | Patanjali/Finn
D2.3 | PTF test and validation |  | Report, dataset | CSV | INCOIS, NGI | M01 | M48 | Patanjali/Finn
D2.3 | PTF test and validation |  | Report, dataset | CSV | INCOIS, NGI | M01 | M48 | Patanjali/Finn
D2.4 | Impact forecasting test and validation |  | Report, datset | CSV | UCL, INCOIS | M01 | M45 | Fatemeh
D2.5 | Uncertainty communication in warnings |  | Report, focus group/interview transcript, focus group/interview audio recording, focus group/interview video recording, survey/online survey | CSV, SAV, doc, wav, mp3, mp4, non-digital paper surveys | UCL, INCOIS | M01 | M48 | Sarah | DMP updated - need to check in as project progresses
D3.1 | Tsunami risk perception and readiness to respond |  | Report, focus group/interview transcript, focus group/interview audio recording, focus group/interview video recording, survey/online survey | CSV, SAV, doc, wav, mp3, mp4, non-digital paper surveys | UCL, INCOIS | M01 | M48 | Sarah | DMP updated - need to check in as project progresses
D3.2 | Inclusivity KPIs |  | Report, focus group |  | UCL, INCOIS | M01 | M45 | Ajay/Sunanda | Co‑design inclusivity markers to complement the 12 Tsunami Ready indicators.
D3.3 | Private Sector engagement and business continuity |  | Table top exercise, focus group |  | UCL, INCOIS | M01 | M42 | Gianluca
D3.4 | Tsunami Ready Kit |  | Report |  | INCOIS, UCL | M01 | M48 | Ajay/Sunanda